## Issues
Description of issue/request | THD's Priority | Handed off to Puppet | THD: ETA on when this will be added/resolved | Puppet Ticket Number | PRODUCT FIELD Status of Request Note: Kim set expectations that these arent commitments or refusals. This is just the status right now. | PRODUCT FIELD Comments from Puppet Product Teams
We cannot use Code Manager because it takes too long in order to pull down all of our Repositories and does not work at all for our Datacenter Ecosystems because we have too many modules. | High | 2019-08-21 | Pending Puppetlabs Engineering decision on when they will resolve this. 4/2 Note: PE 2019.5 has improvements to be tested by THD. | Support Ticket: 35972 | 7/1 - Added to productboard - Feature delivered, awaiting customer validation | NW: THD needs to test the new modules deployment API in PE 2019.4+
Puppet Upgrades are troublesome, there are many ways to upgrade the Puppet Infrastructure and we still run into issues. Example not all sites are using Code Manager but the installer thinks that it does, also the documented process is to use a answers file that is cumbersome. | Medium |  |  |  | 7/1 - Added to productboard - Making improvements - Product should discuss specific needs with customer | ML: I am starting to look into what makes upgrades hard, if they have a list or something of what makes upgrades difficult I would love to see this. I am also happy to talk with them about this topic if that makes sense.
Self-healing in Puppet, currently there is no self-healing ability in Puppet for known issues. We are requesting that self-healing be added into Puppet Enterprise we have examples we can show of what we are doing here. | Medium |  |  |  | 7/1 - Added to productboard - Not prioritized - Product should discuss specific needs with customer | JG: 7/1 We should discuss this with them. The right PM would likely be Carl.
There is no Puppet Orchestrator status or Agent status on the Puppet Console for how many servers are connected to each compile master for Orchestrator and how many are not connected but in the inventory. | High |  | 4/2 discussed with Nick and Patrick. |  | 7/1 - Added to productboard - Not prioritized | JG: 7/1 This is not prioritized but is reasonable. I have no questions about these requirements. This has been added to a backlog for UI improvements. This is not the top priority in that list presently so there is no release vehicle for this today.
Even though the Puppet core services might be running there maybe an issue with the service and the Puppet Console states that everything is Green when in reality it's not. | High |  | 4/2 discussed with Nick and Patrick. Continuing discussions on TAM calls. |  | 7/1 - Added to productboard - Not prioritized | NW: Status widget will show green when for example puppetdb has a problem connecting to postgresql... or similarly the orchestrator shows green but looking at the status API is does show it shouldn't be. JG: 7/1 This is not prioritized but is reasonable. I have no questions about these requirements. This has been added to a backlog for UI improvements. This is not the top priority in that list presently so there is no release vehicle for this today.
Currently there is not a way to identify that an Orchestrator token is still good or how many days/hours/etc.. It has left in order to setup automation to auto-generate tokens for Orchestrator. The current way is to use the token to hit an API endpoint and wait for it to say it couldn't authenticate. | High |  |  |  | 7/1 - Added to productboard - Not prioritized | JG: 7/1 This is not prioritized but is reasonable. I have no questions about these requirements. This has been added to a backlog for cert management improvements. This is not the top priority in that list presently so there is no release vehicle for this today. JN: 7/1 There is an existing API for retrieving token status in RBAC and it is publicly documented: https://puppet.com/docs/pe/2019.8/rbac_api_v2_tokens_endpoints.html#rbac_api_v2_auth_token_auth_post
We currently do not see a way to filter on a Puppet Job for hundreds of nodes to quickly identifies which ones failed and why without having to do a lot of work, or using the API. We would like to see something via the Puppet Console. | Low |  |  |  | 7/1 - Added to productboard - Not prioritized | JG: 7/1 This is not prioritized but is reasonable. I have no questions about these requirements. This has been added to a backlog for UI improvements. This is not the top priority in that list presently so there is no release vehicle for this today.
There is currently not a way for PDK to test via onceover using PDK to test duplicate declarations in modules. | Medium |  |  |  | 7/1 - Added to productboard - Not prioritized | JG: 7/1 This not prioritized. We're in between PM's for this area of the product at the moment, so this may take a bit to get thought through.
There is currently not a way for PDK to test the control repository to ensure the Puppetfile, hieradata, and roles/profiles are using the proper syntax. | Medium |  |  |  | 7/1 - Added to productboard - Not prioritized | JG: 7/1 This not prioritized. We're in between PM's for this area of the product at the moment, so this may take a bit to get thought through.
There is not a good way to filter in Puppet Orchestrator for tasks that were written by a customer or pulled from the forge. | Medium |  |  |  | 7/1 - Added to productboard - Not prioritized - Product should discuss specific needs with customer | JG: 7/1 This is not prioritized but is reasonable. I have no questions about these requirements. This has been added to a backlog for UI improvements. This is not the top priority in that list presently so there is no release vehicle for this today.
There isn't a way to export the puppet jobs that have ran into a file that can be emailed to customers via the Puppet Console. | Low |  |  |  | 7/1 - Added to productboard - Not prioritized - Product should discuss specific needs with customer | JG: 7/1 This is not prioritized but is reasonable. I have no questions about these requirements. This has been added to a backlog for UI improvements. This is not the top priority in that list presently so there is no release vehicle for this today.
Puppet Orchestrator has a queing issue when we run a high number of systems in one puppet task. So if I run 1499 systems in one puppet task it uses all 250 concurrent jobs and everything queues up until a slot is free from the job that had 1499 systems. | High |  |  |  | 7/1 - Added to productboard - Not prioritized - Product should discuss specific needs with customer | JG: 7/1 This is not prioritized but is reasonable. We'd need to get feedback on how you'd want to handle throttling these jobs. The correct PM is Nick Walker.
Puppet Orchestrator does not have a way to give a count of how many jobs are using the 250 slots, and which jobs are queued up behind it via an API. | High |  |  |  | 7/1 - Added to productboard - Not prioritized - Product should discuss specific needs with customer | JG: 7/1 This is not prioritized but is reasonable. We'd need to get feedback on how you'd want to handle throttling these jobs. The correct PM is Nick Walker.
What's the best way to upgrade Agents? |  |  |  |  | 7/1 - Added to productboard - Not prioritized | JG: 7/1 This row is a comment, not a request but I added it to product board. What im taking away from this is we need prescriptive documentation for the best way to do this.
Node Graph Deprecation and functionality Support ticket: 39583 - Puppet resources.dot files (https://puppetlabs.zendesk.com/agent/tickets/39583) PE-29474 Enhancing resources.dot related features and Node Graph (https://tickets.puppetlabs.com/browse/PE-29474) Quote from Patrick at THD: “If this is something that Puppetlabs is depreciating I understand but I feel saddened by the fact that instead of improving a tool Puppetlabs has decided to completely get rid of it. I am formally requesting to have some way via the Puppet Console that can be exported to customers that will provide resource dependency in an easily digestible form (potentially from PuppetDB Report).“ | TBD |  |  | Supp Ticket: 39583 Jira: PE-29474 | 7/1 - Added to productboard - Not prioritized - Product should discuss specific needs with customer | JG: 7/1 Jonny is the PM for compliance, I chatted with him today and he confirmed. We should have him chat with them about their SOX reporting needs. Context will not be to rehash a decision about node graph, solution will not be node graph.

## Wish List
Description of issue/request | Handed off to Puppet | ETA on when this will be added/resolved | Puppet Ticket Number | Comments from Puppet Product Teams (Yes, No, Mabye)
A copy of the PDX videos/slides that were shown/recoreded at PDX this year
I want a dashboard that tells me what every agent is doing, where it is in a run if there is one, how long that step has been running, how long the run has been happening, etc …. preferably with an API so I can interact with the backend directly
It would be nice if there was a tool that customers could use to create modules without having to write puppet code.
We would like a new resource or someway of posting an error (exit code 1) but still continue to compile, currently ware using notify then running an exec to /bin/false which is not great | 2018-10-04 | Unkown | PUP-9208
It would be nice if via the Puppet Console we could filter on the Puppet Infrastructure logs to search for errors, then have it send an email, or open a ticket in Service Now, or post to Slack
We would like to have puppet check for items like: "is the puppetserver consuming all the java memory" and "if garbage collection is more often than the other servers that are doing garbage collection." For the puppet processes we would like health checks to ensure the system is healthy from a puppet point of view
It would be nice if we had a way customers could search for an rpm name to see what module it belongs to without needing to be logged into the console or using GitHub. Example ntp-4.1.1-1.x86-64.rpm is in ntp::v1_0_0
I want a way to upload a list of systems into Orchestrator from a file then Orchestrator can then populate the list of servers to run against.
It would be nice if we could schedule jobs in Puppet Orchestrator in 2019.1.x and above on specific days, like every second Tuesday of every month at 2AM.
It would be nice if there was a GoLang library that could be used to run tasks, get orchestraton tasks, and able to hit and get responses from all Console/PuppetDB/Orchestration APIs. Then we could pass the orchestrator/puppetdb/console hostname and port and it would all work without needing to know specifically how to call an API or that it was depreciated for a newer one
A list of commonly used jobs, with as much as possible pre-populated (like the compile master node list) for Puppet Orchestrator jobs.
Multiple back ends other than just file, for example databases that have values or API calls, or JSON requests.
Query system to come up with a puppet module that can be used to stand up an idenitcal server

## Software Integration
Application Name
Concourse
GitHub
GitLab
Google Cloud Platform (GCP)
Jenkins
Kubernets
Qualys
Service Now
Slack
Looker
Pivotal Cloud Foundary (PCF)
Notifier
Big Query