## Issues Tracking_10.21
Issue/Use Case | THD's Priority | Current Status | Date Added | Source | THD: ETA on when this will be added/resolved | Puppet/Jira Ticket Numbers | PRODUCT FIELD Status of Request Note: 07.01.2021 | PRODUCT FIELD Comments from Puppet Product Teams | Status 6/16/21 | Margaret's notes from convo with THD 1/7
We cannot use Code Manager because it takes too long in order to pull down all of our Repositories and does not work at all for our Datacenter Ecosystems because we have too many modules. Read more here | TOP 1 | Waiting for test | 2019-08-21 |  | Pending Puppetlabs Engineering decision on when they will resolve this. 4/2 Note: PE 2019.8.5 has improvements to be tested by THD. | Supp Tickets: 35972, #39833 Jira: CODE7/19MGMT-1299, CODEMGMT-1415 | 7/1 - Added to productboard - Feature delivered, awaiting customer validation | NW: THD needs to test the new modules deployment API in PE 2019.4+ | Partially completed. DIO reached out to me on 11/19/20 that they would like testing against LTS (2019.8.x) regarding CodeManager. R10k work is in sprint
Self-healing in Puppet, currently there is no self-healing ability in Puppet for known issues. We are requesting that self-healing be added into Puppet Enterprise we have examples we can show of what we are doing here. | Top 2 | On Product Board |  |  |  |  | 7/1 - Added to productboard - Not prioritized - Product should discuss specific needs with customer | JG: 7/1 We should discuss this with them. The right PM would likely be Carl. | https://portal.productboard.com/puppet/1-puppet-idea-portal/c/42-self-healing | in backlog, not roadmap
Puppet Upgrades are troublesome, there are many ways to upgrade the Puppet Infrastructure and we still run into issues. Example not all sites are using Code Manager but the installer thinks that it does, also the documented process is to use a answers file that is cumbersome. | Top 3 | Better installs lately, look at using PEADM |  |  |  |  | 7/1 - Added to productboard - Making improvements - Product should discuss specific needs with customer | ML: I am starting to look into what makes upgrades hard, if they have a list or something of what makes upgrades difficult I would love to see this. I am also happy to talk with them about this topic if that makes sense. | https://portal.productboard.com/puppet/1-puppet-idea-portal/c/48-upgrade-improvements-for-2019-8
Metrics -- to get indication how env is behaving in real-time. How do I know volume is happening and not hitting a threshold. Some way of looking at the environment to see not exceeding AFTER they made changes! How Many Jruby used, CPU usage? How to get something like that on the Console → very custom specific; THD is aware of that, but a baseline would be helpful that the customer can adjust/modify based on their environment. | Top 4 | 2019.8.8 metrics collector - The Puppet metrics collector module is now included in PE installations and upgrades. The module collects Puppet metrics by default, but system metrics collection is disabled. The Metrics collector module needs to be installed by Home Depot | 2020-08-20 | TAM Call |  |  | SKP: Kim add to product board |  | https://forge.puppet.com/modules/puppetlabs/puppet_metrics_collector | what metrics are red/green/yellow. does it send alerts. or can it be built into alerts. need someone that is watching it. context around what is wrong and what to fix.
There is no Puppet Orchestrator status or Agent status on the Puppet Console for how many servers are connected to each compile master for Orchestrator and how many are not connected but in the inventory. | High | Currently open |  |  | 4/2 discussed with Nick and Patrick. |  | 7/1 - Added to productboard - Not prioritized | JG: 7/1 This is not prioritized but is reasonable. I have no questions about these requirements. This has been added to a backlog for UI improvements. This is not the top priority in that list presently so there is no release vehicle for this today. | some api for it - skeletor. do they know why the agent is getting disconnected? | do they have 200 agents not connected or not working properly. are compilers healthy. is it not communicating back to primary. apis are not, but wanting to have something to know. they get told that puppet is broken, want to be proactive about fixing things that are broken. be able to be proactive with their users. have to figure out what is up or down, then figure out what is down.
Even though the Puppet core services might be running there maybe an issue with the service and the Puppet Console states that everything is Green when in reality it's not. | High | Need to see more information on this |  |  | 4/2 discussed with Nick and Patrick. Continuing discussions on TAM calls. |  | 7/1 - Added to productboard - Not prioritized | NW: Status widget will show green when for example puppetdb has a problem connecting to postgresql... or similarly the orchestrator shows green but looking at the status API is does show it shouldn't be. JG: 7/1 This is not prioritized but is reasonable. I have no questions about these requirements. This has been added to a backlog for UI improvements. This is not the top priority in that list presently so there is no release vehicle for this today. | maybe a bug if it doesn't match the API. | there are errors in the log that it is not actually working correctly. since PE 2017. but api and widget say it's green. what info do we need if they run into this again? what logs do we need? what do our engineers need to look into this? service could be having problems but it still says okay. what service is failing. logs that demonstrate that it is a failure, plus the console services logs. it may be that the service is having issues, but it's not reporting that it is down. mostly a heartbeat kind of thing
Currently there is not a way to identify that an Orchestrator token is still good or how many days/hours/etc.. It has left in order to setup automation to auto-generate tokens for Orchestrator. The current way is to use the token to hit an API endpoint and wait for it to say it couldn't authenticate. | High | Complete; demo'd by Paul |  |  |  |  | 7/1 - Added to productboard - Not prioritized | JG: 7/1 This is not prioritized but is reasonable. I have no questions about these requirements. This has been added to a backlog for cert management improvements. This is not the top priority in that list presently so there is no release vehicle for this today. JN: 7/1 There is an existing API for retrieving token status in RBAC and it is publicly documented: https://puppet.com/docs/pe/2019.8/rbac_api_v2_tokens_endpoints.html#rbac_api_v2_auth_token_auth_post | Token status in RBAC 2019.8.x https://puppet.com/docs/pe/2019.8/rbac_api_v2_tokens_endpoints.html#rbac_api_v2_auth_token_auth_post | work with orchestrator token be listed on the tokens? don't log in to console for weeks at a time. API mostly. having an option to when these are about to expire here is the alert path. send to pager duty or something. proactive notification. want an automated way to manage these in the tool. orchestrator token will be there. they will need to know who created the token and then they can see it under the token page. they can add a description when creating the token to clear up any questions
We currently do not see a way to filter on a Puppet Job for hundreds of nodes to quickly identifies which ones failed and why without having to do a lot of work, or using the API. We would like to see something via the Puppet Console. | Low | Complete? Job filtering demo'd by Paul previously and this is in 2019.8.6; Need confirmation from Home Depot |  |  |  |  | 7/1 - Added to productboard - Not prioritized | JG: 7/1 This is not prioritized but is reasonable. I have no questions about these requirements. This has been added to a backlog for UI improvements. This is not the top priority in that list presently so there is no release vehicle for this today. | Need some clarification from them. Filter is available in 2019.8.4 | give me all r10k runs. what are the reasons for failing. make this easy. how many times did the x module fail? wildcard search. API first, then GUI. filter/searching across all jobs.
There is currently not a way for PDK to test via onceover using PDK to test duplicate declarations in modules. | Medium | Currently open; discussed with Ben+Dillon need to convince Ben |  |  |  |  | 7/1 - Added to productboard - Not prioritized | JG: 7/1 This not prioritized. We're in between PM's for this area of the product at the moment, so this may take a bit to get thought through. | Ben Ford or Matt Young?
There is currently not a way for PDK to test the control repository to ensure the Puppetfile, hieradata, and roles/profiles are using the proper syntax. | Medium | [5 empty] | 7/1 - Added to productboard - Not prioritized | JG: 7/1 This not prioritized. We're in between PM's for this area of the product at the moment, so this may take a bit to get thought through. | Ben Ford or Matt Young?
There is not a good way to filter in Puppet Orchestrator for tasks that were written by a customer or pulled from the forge. | Medium | What are you trying to solve for in this request? |  |  |  |  | 7/1 - Added to productboard - Not prioritized - Product should discuss specific needs with customer | JG: 7/1 This is not prioritized but is reasonable. I have no questions about these requirements. This has been added to a backlog for UI improvements. This is not the top priority in that list presently so there is no release vehicle for this today. | why do they want to do this? what problem does this solve?
There isn't a way to export the puppet jobs that have ran into a file that can be emailed to customers via the Puppet Console. | Low | Can export report -> by run status/fact; Need more information? |  |  |  |  | 7/1 - Added to productboard - Not prioritized - Product should discuss specific needs with customer | JG: 7/1 This is not prioritized but is reasonable. I have no questions about these requirements. This has been added to a backlog for UI improvements. This is not the top priority in that list presently so there is no release vehicle for this today. | Single job can be exported from the GUI. | long term - exporting more than 1 job. can they do this via the API? Automated results export. developers create SNOW change request, do the execution, run puppet, did it pass fail, then collect data and build a report. want to be able to filter the data for just what they need. take data for all jobs and write back to SNOW. been doing this 4-5 years.
Puppet Orchestrator has a queing issue when we run a high number of systems in one puppet task. So if I run 1499 systems in one puppet task it uses all 250 concurrent jobs and everything queues up until a slot is free from the job that had 1499 systems. Read more here | High | Product is aware and this is being prioritized, this is valuable feature request |  |  |  | Supp Ticket: 37030 Jira: PE-29426 | 7/1 - Added to productboard - Not prioritized - Product should discuss specific needs with customer | JG: 7/1/2020 This is not prioritized but is reasonable. We'd need to get feedback on how you'd want to handle throttling these jobs. The correct PM is Nick Walker. | https://portal.productboard.com/puppet/1-puppet-idea-portal/c/191-orchestrator-command-deploy-parity-with-mcollective-puppet-agent there is a command deploy endpoint to deploy the endpoint.--tags for command/deploy to help home depot mitigate this. this can be done via the API. can they try this. nick mentioned this in the past | SNOW coming into puppet. any given night they have 50-100 changes, 1-1,000 systems. when they queue up. it can take forever. first in first out? first come first serve? how to keep up with who is in the queue? did 450k automated deploys at a queue of 250 in one quarter. ton of queing. it's a bottleneck. can they run a lot more jobs thorugh it. what is the fall over point? roadmap - can we increase # of concurrent jobs that can be processed. Looking at Jira Ticket likely has the answer
Puppet Orchestrator does not have a way to give a count of how many jobs are using the 250 slots, and which jobs are queued up behind it via an API. | High | Open; "How can I queue jobs in orchestrator"; could use Bolt? |  |  |  |  | 7/1 - Added to productboard - Not prioritized - Product should discuss specific needs with customer | JG: 7/1 This is not prioritized but is reasonable. We'd need to get feedback on how you'd want to handle throttling these jobs. The correct PM is Nick Walker. | https://portal.productboard.com/puppet/1-puppet-idea-portal/c/191-orchestrator-command-deploy-parity-with-mcollective-puppet-agent
What's the best way to upgrade Agents? | Closed | Believe this should be Closed; Paul discussed with THD in may/april ref: https://puppet.com/docs/pe/2019.8/upgrading_agents.html ;no more quantifiable action that can be done. |  |  |  |  | 7/1 - Added to productboard - Not prioritized | JG: 7/1 This row is a comment, not a request but I added it to product board. What im taking away from this is we need prescriptive documentation for the best way to do this. | https://puppet.com/docs/pe/2019.8/upgrading_agents.html | module - it has it all pointing to the compiler and that is 20k servers that need to run the puppet agent. it is more effecient to use satellite or yum update. it handles the load better. their scale will break the server trying to update all of them. need to go into a scalable repo - do security planing before, audit trail, sox compliance, all gets done in the repo - if they run the module it bypasses all this, so it does not work. puppet agent - sign with an internal key, then send to their repo, scan with internal keys for risk, then tag that version and deploy out. sometimes there has to be a config change, sometimes make changes. can't cook in the oven if you are cleaning. shell scripts, ansible, to make it easy on them. tried plans? teams are more familar with anisble and terraform, what does bolt provide over ansible to make people switch. every time they add something new they need to maintain that is money is pocket.
Node Graph Deprecation and functionality Support ticket: 39583 - Puppet resources.dot files PE-29474 Enhancing resources.dot related features and Node Graph Quote from Patrick at THD: “If this is something that Puppetlabs is depreciating I understand but I feel saddened by the fact that instead of improving a tool Puppetlabs has decided to completely get rid of it. I am formally requesting to have some way via the Puppet Console that can be exported to customers that will provide resource dependency in an easily digestible form (potentially from PuppetDB Report).“ | CLOSED | Not coming back per product |  |  |  | Supp Ticket: 39583 Jira: PE-29474 | 7/1 - Added to productboard - Not prioritized - Product should discuss specific needs with customer | JG: 7/1 Jonny is the PM for compliance, I chatted with him today and he confirmed. We should have him chat with them about their SOX reporting needs. Context will not be to rehash a decision about node graph, solution will not be node graph. | Node Graph is not being added back. | how do i easily get info to a customer about what is being installed on the system. if they have 200 modules on the system - puppet should know what is being installed and be able to provide this. and be able to search. what module has ntp? there are 6. why do they have 6. how do we collect and leverage metadata. what does it all mean. meta data for what is happen. with this how do they drive more efficiency. a lot of aggreagation to get the metadata to drive efficiency. what is going to change. every puppet thing needs to come together as a unit

## Issues
2021-08-21 | THD's Priority | Handed off to Puppet | THD: ETA on when this will be added/resolved | Puppet/Jira Ticket Numbers | PRODUCT FIELD Status of Request Note: Kim set expectations that these arent commitments or refusals. This is just the status right now. | PRODUCT FIELD Comments from Puppet Product Teams | Status 6/16/21 | Margaret's notes from convo with THD 1/7
We cannot use Code Manager because it takes too long in order to pull down all of our Repositories and does not work at all for our Datacenter Ecosystems because we have too many modules. Read more here | TOP 1 | 2019-08-21 | Pending Puppetlabs Engineering decision on when they will resolve this. 4/2 Note: PE 2019.8.5 has improvements to be tested by THD. | Supp Tickets: 35972, #39833 Jira: CODE7/19MGMT-1299, CODEMGMT-1415 | 7/1 - Added to productboard - Feature delivered, awaiting customer validation | NW: THD needs to test the new modules deployment API in PE 2019.4+ | Partially completed. DIO reached out to me on 11/19/20 that they would like testing against LTS (2019.8.x) regarding CodeManager. R10k work is in sprint
Self-healing in Puppet, currently there is no self-healing ability in Puppet for known issues. We are requesting that self-healing be added into Puppet Enterprise we have examples we can show of what we are doing here. | Top 2 |  |  |  | 7/1 - Added to productboard - Not prioritized - Product should discuss specific needs with customer | JG: 7/1 We should discuss this with them. The right PM would likely be Carl. | https://portal.productboard.com/puppet/1-puppet-idea-portal/c/42-self-healing | in backlog, not roadmap
Puppet Upgrades are troublesome, there are many ways to upgrade the Puppet Infrastructure and we still run into issues. Example not all sites are using Code Manager but the installer thinks that it does, also the documented process is to use a answers file that is cumbersome. | Top 3 |  |  |  | 7/1 - Added to productboard - Making improvements - Product should discuss specific needs with customer | ML: I am starting to look into what makes upgrades hard, if they have a list or something of what makes upgrades difficult I would love to see this. I am also happy to talk with them about this topic if that makes sense. | https://portal.productboard.com/puppet/1-puppet-idea-portal/c/48-upgrade-improvements-for-2019-8
Metrics -- to get indication how env is behaving in real-time. How do I know volume is happening and not hitting a threshold. Some way of looking at the environment to see not exceeding AFTER they made changes! How Many Jruby used, CPU usage? How to get something like that on the Console → very custom specific; THD is aware of that, but a baseline would be helpful that the customer can adjust/modify based on their environment. | Top 4 | August 20, 2020 (TAM call) |  |  | SKP: Kim add to product board |  | https://forge.puppet.com/modules/puppetlabs/puppet_metrics_collector | what metrics are red/green/yellow. does it send alerts. or can it be built into alerts. need someone that is watching it. context around what is wrong and what to fix.
There is no Puppet Orchestrator status or Agent status on the Puppet Console for how many servers are connected to each compile master for Orchestrator and how many are not connected but in the inventory. | High |  | 4/2 discussed with Nick and Patrick. |  | 7/1 - Added to productboard - Not prioritized | JG: 7/1 This is not prioritized but is reasonable. I have no questions about these requirements. This has been added to a backlog for UI improvements. This is not the top priority in that list presently so there is no release vehicle for this today. | some api for it - skeletor. do they know why the agent is getting disconnected? | do they have 200 agents not connected or not working properly. are compilers healthy. is it not communicating back to primary. apis are not, but wanting to have something to know. they get told that puppet is broken, want to be proactive about fixing things that are broken. be able to be proactive with their users. have to figure out what is up or down, then figure out what is down.
Even though the Puppet core services might be running there maybe an issue with the service and the Puppet Console states that everything is Green when in reality it's not. | High |  | 4/2 discussed with Nick and Patrick. Continuing discussions on TAM calls. |  | 7/1 - Added to productboard - Not prioritized | NW: Status widget will show green when for example puppetdb has a problem connecting to postgresql... or similarly the orchestrator shows green but looking at the status API is does show it shouldn't be. JG: 7/1 This is not prioritized but is reasonable. I have no questions about these requirements. This has been added to a backlog for UI improvements. This is not the top priority in that list presently so there is no release vehicle for this today. | maybe a bug if it doesn't match the API. | there are errors in the log that it is not actually working correctly. since PE 2017. but api and widget say it's green. what info do we need if they run into this again? what logs do we need? what do our engineers need to look into this? service could be having problems but it still says okay. what service is failing. logs that demonstrate that it is a failure, plus the console services logs. it may be that the service is having issues, but it's not reporting that it is down. mostly a heartbeat kind of thing
Currently there is not a way to identify that an Orchestrator token is still good or how many days/hours/etc.. It has left in order to setup automation to auto-generate tokens for Orchestrator. The current way is to use the token to hit an API endpoint and wait for it to say it couldn't authenticate. | High |  |  |  | 7/1 - Added to productboard - Not prioritized | JG: 7/1 This is not prioritized but is reasonable. I have no questions about these requirements. This has been added to a backlog for cert management improvements. This is not the top priority in that list presently so there is no release vehicle for this today. JN: 7/1 There is an existing API for retrieving token status in RBAC and it is publicly documented: https://puppet.com/docs/pe/2019.8/rbac_api_v2_tokens_endpoints.html#rbac_api_v2_auth_token_auth_post | Token status in RBAC 2019.8.x https://puppet.com/docs/pe/2019.8/rbac_api_v2_tokens_endpoints.html#rbac_api_v2_auth_token_auth_post | work with orchestrator token be listed on the tokens? don't log in to console for weeks at a time. API mostly. having an option to when these are about to expire here is the alert path. send to pager duty or something. proactive notification. want an automated way to manage these in the tool. orchestrator token will be there. they will need to know who created the token and then they can see it under the token page. they can add a description when creating the token to clear up any questions
We currently do not see a way to filter on a Puppet Job for hundreds of nodes to quickly identifies which ones failed and why without having to do a lot of work, or using the API. We would like to see something via the Puppet Console. | Low |  |  |  | 7/1 - Added to productboard - Not prioritized | JG: 7/1 This is not prioritized but is reasonable. I have no questions about these requirements. This has been added to a backlog for UI improvements. This is not the top priority in that list presently so there is no release vehicle for this today. | Need some clarification from them. Filter is available in 2019.8.4 | give me all r10k runs. what are the reasons for failing. make this easy. how many times did the x module fail? wildcard search. API first, then GUI. filter/searching across all jobs.
There is currently not a way for PDK to test via onceover using PDK to test duplicate declarations in modules. | Medium |  |  |  | 7/1 - Added to productboard - Not prioritized | JG: 7/1 This not prioritized. We're in between PM's for this area of the product at the moment, so this may take a bit to get thought through. | Ben Ford or Matt Young?
There is currently not a way for PDK to test the control repository to ensure the Puppetfile, hieradata, and roles/profiles are using the proper syntax. | Medium |  |  |  | 7/1 - Added to productboard - Not prioritized | JG: 7/1 This not prioritized. We're in between PM's for this area of the product at the moment, so this may take a bit to get thought through. | Ben Ford or Matt Young?
There is not a good way to filter in Puppet Orchestrator for tasks that were written by a customer or pulled from the forge. | Medium |  |  |  | 7/1 - Added to productboard - Not prioritized - Product should discuss specific needs with customer | JG: 7/1 This is not prioritized but is reasonable. I have no questions about these requirements. This has been added to a backlog for UI improvements. This is not the top priority in that list presently so there is no release vehicle for this today. | why do they want to do this? what problem does this solve?
There isn't a way to export the puppet jobs that have ran into a file that can be emailed to customers via the Puppet Console. | Low |  |  |  | 7/1 - Added to productboard - Not prioritized - Product should discuss specific needs with customer | JG: 7/1 This is not prioritized but is reasonable. I have no questions about these requirements. This has been added to a backlog for UI improvements. This is not the top priority in that list presently so there is no release vehicle for this today. | Single job can be exported from the GUI. | long term - exporting more than 1 job. can they do this via the API? Automated results export. developers create SNOW change request, do the execution, run puppet, did it pass fail, then collect data and build a report. want to be able to filter the data for just what they need. take data for all jobs and write back to SNOW. been doing this 4-5 years.
Puppet Orchestrator has a queing issue when we run a high number of systems in one puppet task. So if I run 1499 systems in one puppet task it uses all 250 concurrent jobs and everything queues up until a slot is free from the job that had 1499 systems. Read more here | High |  |  | Supp Ticket: 37030 Jira: PE-29426 | 7/1 - Added to productboard - Not prioritized - Product should discuss specific needs with customer | JG: 7/1 This is not prioritized but is reasonable. We'd need to get feedback on how you'd want to handle throttling these jobs. The correct PM is Nick Walker. | https://portal.productboard.com/puppet/1-puppet-idea-portal/c/191-orchestrator-command-deploy-parity-with-mcollective-puppet-agent there is a command deploy endpoint to deploy the endpoint.--tags for command/deploy to help home depot mitigate this. this can be done via the API. can they try this. nick mentioned this in the past | SNOW coming into puppet. any given night they have 50-100 changes, 1-1,000 systems. when they queue up. it can take forever. first in first out? first come first serve? how to keep up with who is in the queue? did 450k automated deploys at a queue of 250 in one quarter. ton of queing. it's a bottleneck. can they run a lot more jobs thorugh it. what is the fall over point? roadmap - can we increase # of concurrent jobs that can be processed. Looking at Jira Ticket likely has the answer
Puppet Orchestrator does not have a way to give a count of how many jobs are using the 250 slots, and which jobs are queued up behind it via an API. | High |  |  |  | 7/1 - Added to productboard - Not prioritized - Product should discuss specific needs with customer | JG: 7/1 This is not prioritized but is reasonable. We'd need to get feedback on how you'd want to handle throttling these jobs. The correct PM is Nick Walker. | https://portal.productboard.com/puppet/1-puppet-idea-portal/c/191-orchestrator-command-deploy-parity-with-mcollective-puppet-agent
What's the best way to upgrade Agents? |  |  |  |  | 7/1 - Added to productboard - Not prioritized | JG: 7/1 This row is a comment, not a request but I added it to product board. What im taking away from this is we need prescriptive documentation for the best way to do this. | https://puppet.com/docs/pe/2019.8/upgrading_agents.html | module - it has it all pointing to the compiler and that is 20k servers that need to run the puppet agent. it is more effecient to use satellite or yum update. it handles the load better. their scale will break the server trying to update all of them. need to go into a scalable repo - do security planing before, audit trail, sox compliance, all gets done in the repo - if they run the module it bypasses all this, so it does not work. puppet agent - sign with an internal key, then send to their repo, scan with internal keys for risk, then tag that version and deploy out. sometimes there has to be a config change, sometimes make changes. can't cook in the oven if you are cleaning. shell scripts, ansible, to make it easy on them. tried plans? teams are more familar with anisble and terraform, what does bolt provide over ansible to make people switch. every time they add something new they need to maintain that is money is pocket.
Node Graph Deprecation and functionality Support ticket: 39583 - Puppet resources.dot files PE-29474 Enhancing resources.dot related features and Node Graph Quote from Patrick at THD: “If this is something that Puppetlabs is depreciating I understand but I feel saddened by the fact that instead of improving a tool Puppetlabs has decided to completely get rid of it. I am formally requesting to have some way via the Puppet Console that can be exported to customers that will provide resource dependency in an easily digestible form (potentially from PuppetDB Report).“ | TBD |  |  | Supp Ticket: 39583 Jira: PE-29474 | 7/1 - Added to productboard - Not prioritized - Product should discuss specific needs with customer | JG: 7/1 Jonny is the PM for compliance, I chatted with him today and he confirmed. We should have him chat with them about their SOX reporting needs. Context will not be to rehash a decision about node graph, solution will not be node graph. | Node Graph is not being added back. | how do i easily get info to a customer about what is being installed on the system. if they have 200 modules on the system - puppet should know what is being installed and be able to provide this. and be able to search. what module has ntp? there are 6. why do they have 6. how do we collect and leverage metadata. what does it all mean. meta data for what is happen. with this how do they drive more efficiency. a lot of aggreagation to get the metadata to drive efficiency. what is going to change. every puppet thing needs to come together as a unit | do they have package management turned on? this would give them visibility into what packages are on each of them