## Features and Bugs
Reference | Date Created | Date Updated | Priority | Current Action Owner | Summary | Description | Current Action | Next Action | Type | Status | Next Action Date | Est. Close | Product | Notes & References | Jira/Product Board Links | FY22 Q4 update | FY22 Q3 | FY22 Q2 | 2020
1 | 2019-08-21 | 2022-01-06 | High | THD | Codemanager runtime | THD cannot use Code Manager because it takes too long in order to pull down all of our Repositories and does not work at all for our Datacenter Ecosystems because we have too many modules. | Awaiting Testing by THD team | THD team test this once upgrade is complete | Request | Planned | 2022-01-15 | FY23Q1 | PE |  | CODEMGMT-1414 CODEMGMT-1299 CODEMGMT-1415 SOLARCH-242 | On hold due to holiday push | Fix pushed in 2019.8.8 PE release, PRiley tested; appear to reduce runtime but needs to be tested in enterprise environment by THD | 06/2021: Partially completed. DIO reached out to me on 11/19/20 that they would like testing against LTS (2019.8.x) regarding CodeManager. R10k work is in sprint | https://docs.google.com/document/d/1Iy868Jyk9nKAg4HB_Gj2eKmKTB0ky_9-G_uy9YBTTrc/edit#heading=h.hnqtkm2lxyge
2 | 2021-10-01 | 2022-01-05 | Medium | Puppet team | ChatOps: Need alerting functionality for CA - API or Push..THD send to slack | 2020-12-30: Paul Riley created Script to check CA certs for Compilers and PE Primary Server | Future review Relay functionality with THD |  | Request | On Hold | FY23Q1 |  | PE | https://github.com/paul-riley/cert-check Overview: Bash based 3.x and newer; Logs and emails based on selections; Works against local ca.pem file and API certs |  | Relay can be constructed/configued to push notification
3 | 2021-10-01 | 2022-01-05 | Medium | Puppet team | Self Healing: Performance Issue Alerting (Auto-detection and remediation) | The system should be able to determine and alert via a log message, email, and the UI that it is having a performance issue. Potentially, looking at how long a job takes to return, coupled with Cpu/Disk/Memory monitoring if the system is starting to utilize more that 90% disk, 90% CPU, and 90% memory | Future review Relay functionality with THD |  | Request | On Hold | FY23Q1 |  | PE | The system should be able to determine and alert via a log message, email, and the UI that it is having a performance issue. Potentially, looking at how long a job takes to return, coupled with Cpu/Disk/Memory monitoring if the system is starting to utilize more that 90% disk,, 90% CPU, and 90% memory | 42-self-healing | Relay can be constructed/configued to perform self-healing functionality. |  | Self-healing in Puppet, currently there is no self-healing ability in Puppet for known issues. We are requesting that self-healing be added into Puppet Enterprise we have examples we can show of what we are doing here. | The system should be able to determine and alert via a log message, email, and the UI that it is having a performance issue. Potentially, looking at how long a job takes to return, coupled with Cpu/Disk/Memory monitoring if the system is starting to utilize more that 90% disk,, 90% CPU, and 90% memory
4 | 2021-10-01 | 2022-01-05 | High | Puppet Development | Ability to set a priority of a task/plan run ¦ Queue jobs in Orchestrator | Puppet Orchestrator does not have a way to give a count of how many jobs are using the 250 slots, and which jobs are queued up behind it via an API. "How can I queue jobs in orchestrator"? Looking to solve for: Puppet Orchestrator has a queuing issue when we run a high number of systems in one puppet task. So if I run 1499 systems in one puppet task it uses all 250 concurrent jobs and everything queues up until a slot is free from the job that had 1499 systems. | In product backlog |  | Improvement | Backlog | TBD |  | PE | https://portal.productboard.com/puppet/1-puppet-idea-portal/c/191-orchestrator-command-deploy-parity-with-mcollective-puppet-agent 2020.07.01 - Jed Greshem - This is not prioritized but is reasonable. We'd need to get feedback on how you'd want to handle throttling these jobs. The correct PM is Nick Walker. | PE-30139 | Margret/Sarah are aware but this is not on the priority roadmap¦ Spoke with support, the JRuby tuning will not work in this instance because it impacts plans and these requests are focused on the puppet tasks |  |  | 2020.07.01 - Jed Greshem - This is not prioritized but is reasonable. We'd need to get feedback on how you'd want to handle throttling these jobs. The correct PM is Nick Walker.
5 | 2021-10-01 | 2021-11-09 | Low | THD | Puppet Orchestrator/Agent status on PE console | There is no Puppet Orchestrator status or Agent status on the Puppet Console for how many servers are connected to each compile master for Orchestrator and how many are not connected but in the inventory. | We can start to iterate towards visibility - THD to check in with microservices team (ref 3.6) |  | Improvement | Planned | 2022-01-31 |  | PE |  | PE-28271 | We expose some metrics about the state of the deploy queue, but not of the task queue today, Jenkins jobs are depend on orchestrator status; DEV+Prod
6 | 2021-02-04 | 2022-01-06 | Low | THD | Orchestrator token status | Currently there is not a way to identify that an Orchestrator token is still good or how many days/hours/etc.. It has left in order to setup automation to auto-generate tokens for Orchestrator. The current way is to use the token to hit an API endpoint and wait for it to say it couldn't authenticate. | Ravi will check back on this |  | Task | In Progress | 2022-01-31 |  | PE | Paul says this is in the API, can this be closed? |  | Ravi to confirm if this is still needed
7 | 2021-10-01 | 2022-01-06 | High | THD | Filter Puppet Orchestrator task to distinguish (created by/origin) | There is not a good way to filter in Puppet Orchestrator for tasks that were written by a customer or pulled from the forge | Connect with Product on this use case: Investigation aid to promote speed of remdediation for fault tasks |  | Improvement | New | 2022-01-31 |  | PE |  |  | Only can filter by basic params is an issue. Investigation aid to promote speed of remdediation for fault tasks
8 | 2021-10-01 |  | Medium | THD | Puppet orchestrator job in progress viewability | Detemine how to view the Identify the 250 jobs in use; want to know when a job that is running is supposed to complete | THD: Need to talk to Kel or Russell to better under the microservice metrics fit in with George's team metrics |  | Improvement | In Progress | 2022-01-15 |  | PE |  |  | We expose some metrics about the state of the deploy queue, but not of the task queue today. We can start with providing the total queue length (number of targets) at a given instant. Is this something that would be helpful for THD as a first step towards solving the Orchestration visibility issues?
9 | 2021-04-29 | 2021-10-18 | Medium | Puppet Development | Set priority of task or plan run | Ability to set priority of task /plan run | In product backlog |  | Epic | Backlog | TBD |  | PE | 5680380 | PE-30139
10 | 2021-10-01 | 2022-01-05 | Medium | Puppet Development | Dashboard view of my environment outside of the console | Want to know the state of my environment at all times. This includes visibility to orchestrator tasks. | Future review with Relay/ Puppet Product |  | Improvement | On hold | FY23Q1 |  | PE |  |  | This information can be pulled into Relay to include the cloud environment. The alternate option would be to review specifics with HDP
11 | 2021-10-01 | 2022-01-06 | Medium | Puppet Development | Onceover integration with PDK | There is currently not a way for PDK to test via onceover using PDK to test duplicate declarations in modules. | PDK is being refactored | Beta 0.1.0 scheduled for release in January. THD to test and provide feedback to Ben Ford | New Feature | In Progress | 2022-02-01 | FY23Q1 | PDK | We are refactoring how PDK works: 1. The new suite of tools will contain smaller and more focused tools that all work together. 2. A major benefit of doing this is that one of first tools we're building (right now) is a runtime manager. This means that we don't have to "include Onceover in the PDK" because the runtime manager will just run Onceover like any other PDK tool. 3. Public Beta will be available in FY23 Q1 | Puppet Content Validator | chat with Ben: Rather than shoehorning more and more things into one massive tool, we're refactoring how it works. 1. The thing we called the PDK is now feature-frozen. It will only get version bumps so that it can continue to test current Puppet. 2. the new suite of tools will contain smaller and more focused tools that all work together 3. A major benefit of doing this is that one of first tools we're building (right now) is a runtime manager which means that we don't have to "include Onceover in the PDK" because the runtime manager will just run Onceover like any other PDK tool. 4. Public beta will arrive in FY 23 Q1
12 | 2021-10-01 | 2021-11-29 | Medium | Puppet Development | PDK testing: Check the syntax matches across all 3 (Puppetfile, Hiera data, and roles/profiles) | There is currently not a way for PDK to test the control repository to ensure the Puppetfile, hieradata, and roles/profiles are using the proper syntax | This is on the roadmap for FY23Q1 |  | New Feature | In Progress | 2022-02-01 | FY23Q2 | PDK |  | Control Repo testing | THD would like to check the syntax matches across all 3 (Puppetfile, Hiera data, and roles/profiles)
13 | 2021-10-01 | 2022-01-05 | Medium | THD | Puppet Core services status | Even though the Puppet core services might be running there maybe an issue with the service and the Puppet Console states that everything is Green when in reality it's not. | THD team validate if issue is resolved this once upgrade is complete | THD team validate if issue is resolved this once upgrade is complete | Bug | Planned | FY23Q1 |  | PE |  |  | Discover service issue via customer contact on failure; PE Console showing green but is not accurately represented; not seeing issue in the past two months; prior the issue was happening up to x2 daily
14 | 2021-05-07 | 2022-01-05 | Low | THD | PDB to talk to multiple Postgres DB | Federated management style, or federated reporting? | John to follow-up on what this is needed in this ask |  | Other | Planned | 2022-01-06 |  | PuppetDB |  | 15862180
15 | 2021-10-07 | 2022-01-05 | Medium | Puppet team | Containerize PE: to help manage upgrading and maintenance of PE | This topic has been broached with other companies. We are building a new platform that is based on K8s. TAM to provide updates as they are availabilty for public consumption | Not on roadmap in current state; new PE platform will address this |  | New Feature | Backlog | TBD |  | PE |  |  | Not on roadmap in current state; new PE platform will address this
16 | 2020-08-20 | 2021-11-29 | Medium | THD | Metrics on environment (real-time) | Metrics -- to get indication how env is behaving in real-time. How do I know volume is happening and not hitting a threshold. Some way of looking at the environment to see not exceeding AFTER they made changes! How Many Jruby used, CPU usage? How to get something like that on the Console → very custom specific; THD is aware of that, but a baseline would be helpful that the customer can adjust/modify based on their environment. | THD enable & test 2019.8.8 metrics collector - The Puppet metrics collector module is now included in PE installations and upgrades. The module collects Puppet metrics by default, but system metrics collection is disabled. |  | Improvement | Planned | 2022-02-01 | FY23Q1 | PE